## Gantt Chart
SDMAY22-30 | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Ara Wirless Senior Design Project Spring Semester |  |  |  |  | COMPANY NAME | [6 empty] | SDMAY22-30
PROJECT MANAGER |  | N/A |  |  |  |  | DATE | [6 empty] | 2022-01-10
Double click date to set it
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION (Days) | PCT OF TASK COMPLETE | January | [19 empty] | Feburary | [19 empty] | March | [24 empty] | April | [19 empty] | May
[6 empty] | 1/3 - 1/7 |  |  |  |  | 1/10 - 1/14 |  |  |  |  | 1/17 - 1/21 |  |  |  |  | 1/24 - 1/28 |  |  |  |  | 1/31 - 2/4 |  |  |  |  | 2/7 - 2/11 |  |  |  |  | 2/14 - 2/18 |  |  |  |  | 2/21 - 2/25 |  |  |  |  | 2/28 - 3/4 |  |  |  |  | 3/7 - 3/11 |  |  |  |  | 3/14 - 3/18 |  |  |  |  | 3/21 - 3/25 |  |  |  |  | 3/28 - 4/1 |  |  |  |  | 4/4 - 4/8 |  |  |  |  | 4/11 - 4/15 |  |  |  |  | 4/18 - 4/22 |  |  |  |  | 4/25 - 4/29 |  |  |  |  | 5/2 - 5/6
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Hardware Team
Order Waterproof Enlcosure | Josh O | 2022-02-02 | 2022-02-04 | 2 | 100% | 5/2 - 5/6 M: Finals Week
Enquire Boyd Lab |  | 2022-02-04 | 2022-02-04 | 0 | 0% | 5/2 - 5/6 M: Finals Week
Sumbit Boyd Lab Job |  | 2022-02-07 | 2022-02-08 | 1 | 0% | 5/2 - 5/6 M: Finals Week
Gather a physical working system | Josh O | 2022-02-07 | 2022-02-14 | 7 | 100% | 5/2 - 5/6 M: Finals Week
Fit hardware into enclosure | Josh G | 2022-02-15 | 2022-02-28 | 13 | 100% | 5/2 - 5/6 M: Finals Week
Iterate enclosure design |  | 2022-02-15 | 2022-03-01 | 16 | 75% | 5/2 - 5/6 M: Finals Week
Order necessary parts | Josh O | 2022-03-01 | 2022-03-03 | 2 | 100% | 5/2 - 5/6 M: Finals Week
Manufacture many more enclosures |  | 2022-03-02 | 2022-04-29 | 57 | 20% | 5/2 - 5/6 M: Finals Week
Screw Components onto layers | Josh N | 2022-03-03 | 2022-03-04 | 1 | 100% | 5/2 - 5/6 M: Finals Week
Cut holes for vent and cables in enclosure | Josh N | 2022-03-07 | 2022-03-11 | 4 | 100% | 5/2 - 5/6 M: Finals Week
Finalize enclosure design |  | 2022-03-07 | 2022-03-11 | 4 | 100% | 5/2 - 5/6 M: Finals Week
Splicing ethernet wires to correct length | Josh G | 2022-03-07 | 2022-03-09 | 2 | 100% | 5/2 - 5/6 M: Finals Week
Getting Power Delivery Setup For Enlocusre | Josh N | 2022-03-28 | 2022-04-08 | 10 | 100% | bar: 3/28 - 4/1 M to 4/4 - 4/8 F
Test UE with Basestation in durham | Josh G | 2022-03-14 | 2022-03-16 | 2 | 25% | 5/2 - 5/6 M: Finals Week
Optimize enclosure for manufacturing |  | 2022-03-14 | 2022-03-31 | 17 | 25% | 5/2 - 5/6 M: Finals Week
Design skylark mounting system | Josh N | 2022-03-21 | 2022-03-25 | 4 | 0% | 5/2 - 5/6 M: Finals Week
Deploy UE on Coover with a webcam | Josh N | 2022-03-21 | 2022-03-25 | 4 | 0% | 5/2 - 5/6 M: Finals Week
Test connection and verify data integrity | Josh G | 2022-03-28 | 2022-04-01 | 3 | 0% | 5/2 - 5/6 M: Finals Week
Software Team
Get Testbed Setup | Josh O | 2022-02-07 | 2022-02-11 | 4 | 100% | 5/2 - 5/6 M: Finals Week
Implement UCS algorithm on UE testbench at Durham | Connor K | 2022-03-07 | 2022-03-28 | 21 | 0% | 5/2 - 5/6 M: Finals Week
Implement LDP algorithm on UE testbench at Durham | Nick G | 2022-03-07 | 2022-03-28 | 21 | 0% | 5/2 - 5/6 M: Finals Week
Implement WFQ algorithm on UE testbench at Durham | Ruofeng G | 2022-03-07 | 2022-03-28 | 21 | 0% | 5/2 - 5/6 M: Finals Week
Implement D2D algorithm on UE testbench at Durham | John L | 2022-03-07 | 2022-03-28 | 21 | 0% | 5/2 - 5/6 M: Finals Week
Verify connection between UE and base station (deployed) | All | 2022-03-28 | 2022-04-04 | 6 | 0% | 5/2 - 5/6 M: Finals Week
Test connection and note perfomance (UCS) | Connor K | 2022-04-04 | 2022-04-15 | 11 | 0% | 5/2 - 5/6 M: Finals Week
Test connection and note perfomance (LDP) | Nick G | 2022-04-04 | 2022-04-15 | 11 | 0% | 5/2 - 5/6 M: Finals Week
Test connection and note perfomance (WFQ) | Ruofeng G | 2022-04-04 | 2022-04-15 | 11 | 0% | 5/2 - 5/6 M: Finals Week
Test connection and note perfomance (D2D) | John L | 2022-04-04 | 2022-04-15 | 11 | 0% | 5/2 - 5/6 M: Finals Week
Test connection and note perfomance in correlation to distance (UCS) | Connor K | 2022-04-11 | 2022-04-29 | 18 | 0% | 5/2 - 5/6 M: Finals Week
Test connection and note perfomance in correlation to distance (LDP) |  | 2022-04-11 | 2022-04-29 | 18 | 0% | 5/2 - 5/6 M: Finals Week
Test connection and note perfomance in correlation to distance (WFQ) |  | 2022-04-11 | 2022-04-29 | 18 | 0% | 5/2 - 5/6 M: Finals Week
Test connection and note perfomance in correlation to distance (D2D) | John L | 2022-04-11 | 2022-04-29 | 18 | 0% | 5/2 - 5/6 M: Finals Week