## Slide 1: Lightning Talk 2
Project Plan

## Slide 2: Task Decomposition
Design an enclosure to hold multiple SDR’s and Intel NUC. (User Equipment aka UE)
Modify srsRAN code to support enclosures of multiple ranges.
Deploy UE’s across Ames
Perform testing on the UE’s (enclosures) to verify proper functionality.
Experiment with open source 5G-and-beyond solutions on the network.

## Slide 3: Milestones, Metrics and Evaluation Criteria
October 29th: Design an enclosure that will contain the Intel NUC, an amplifier, and 4 SDRs; B210, N320, X410, and Skylark mMIMO.
November 29th: Test the UE in the lab for reliability and stability
December 14th: Demo the UE enclosure to the National Science Foundation
February 15th: Deploy UE’s across Ames and ISU and get measurements or reliability
March 15th: Experiment with 5G-and-beyond software platforms
April 1st: Conduct performance measurement
April 29th: Demonstration/Report

## Slide 4: Timeline
* August - September 2021: Study basics of the ARA project (https://arawireless.org) and related 5G-and-beyond hardware and software platforms
* October – November 2021: Develop hardware integration and manufacturing strategies for ARA user equipment; deployment of ARA base station equipment; perform initial testing;
* December 2021: Deploy ARA user equipment across City of Ames and ISU Research and Teaching Farms and conduct performance measurement;
* January - February 2022: Participate in the preparation of the ARA deployment around the ISU Curtiss Farm as well as Agronomy and Ag Engineering Farm; Experiment with open-source 5G-and-beyond software platforms using ARA;
* March – April 2022: Experiment with novel 5G-and-beyond solutions and conduct performance measurement; demonstration and report.

## Slide 5: Risks and Risk Management
Enclosure
Equipment breaks: 1%
3D printing errors: 15%

## Slide 6: Effort
3D-model an enclosure | 30 hours
Modifying the srsRAN codebase for each UE | 60 hours
Deploying the UE | 5 hours
Testing UE in the lab and in the field | 30 hours